## Slide 1
ONBOARDING PROGRAMME | MODULE 1
Scrum Fundamentals
How we plan, deliver and continuously improve value in short, focused Sprints
Training pack for new project team members
September 2026
Notes: Welcome the group. Purpose: give every new joiner a shared, accurate understanding of Scrum as defined in the 2020 Scrum Guide, and how we apply it on our projects. Duration: approximately 90 minutes including exercises.

## Slide 2
AGENDA
Scrum Fundamentals | Onboarding
This module covers the Scrum framework end to end, from principles to your first 30 days
Source: The Scrum Guide, K. Schwaber & J. Sutherland (November 2020); team analysis
2
01
Why Scrum
How empirical delivery differs from predictive planning
02
The framework at a glance
One view of how the pieces connect
03
Foundations
Three pillars and five values
04
The Scrum Team
Product Owner, Scrum Master and Developers
05
Events and artefacts
Timeboxes, purposes and commitments
06
Working in practice
User stories, metrics and common pitfalls
07
Your first 30 days
What to expect and what we expect of you
Notes: Walk through the agenda. Emphasise that the session is practical: by the end, participants should be able to take part in every Scrum event with confidence.

## Slide 3
WHY SCRUM
Scrum Fundamentals | Onboarding
Scrum replaces up-front prediction with short feedback loops, reducing delivery risk in complex work
Source: The Scrum Guide, K. Schwaber & J. Sutherland (November 2020); team analysis
3
Predictive (traditional)
Empirical (Scrum)
Planning
Detailed plan fixed at the start
Plan refined every Sprint as we learn
Scope
Locked early; change is costly
Emerges and is reprioritised by value
Feedback
Arrives late, often at user testing
Every Sprint, from real stakeholders
Risk
Discovered late, when it is expensive
Surfaced early through working increments
Value
Delivered in one release at the end
Delivered incrementally, from Sprint 1
Scrum is best suited to complex work where requirements and solutions are uncertain; it is a lightweight framework, not a full methodology.
Notes: Key message: Scrum does not remove planning, it distributes planning across the project. Ask the group for an example of a project where late feedback caused rework.

## Slide 4
THE FRAMEWORK AT A GLANCE
Scrum Fundamentals | Onboarding
Each Sprint is a complete inspect-and-adapt cycle that turns backlog items into a usable Increment
Source: The Scrum Guide, K. Schwaber & J. Sutherland (November 2020); team analysis
4
Product Backlog
Ordered list of everything the product needs
Sprint Planning
Team agrees the Sprint Goal and selects work
Sprint Backlog
Sprint Goal, selected items and delivery plan
The Sprint
1–4 weeks, with a 15-minute Daily Scrum every day
Increment
Usable output that meets the Definition of Done
Sprint Retrospective
Improve how we work
Sprint Review
Inspect outcome with stakeholders
Feedback and improvements feed the next Sprint
So what? Refinement of the Product Backlog happens continuously throughout the Sprint, so that the next Sprint Planning starts with items that are clear, small and ready.
Notes: This is the most important slide of the module. Trace one backlog item from the Product Backlog through to the Increment and then show how Review and Retrospective feed the next Sprint.

## Slide 5
FOUNDATIONS
Scrum Fundamentals | Onboarding
Three empirical pillars make Scrum work; five shared values make the pillars possible
Source: The Scrum Guide, K. Schwaber & J. Sutherland (November 2020); team analysis
5
Transparency
Work and progress are visible to those doing it and those receiving it. Hidden problems cannot be fixed.
Inspection
Artefacts and progress towards goals are inspected frequently to detect variances early.
Adaptation
When something drifts off course, the team adjusts as soon as possible to minimise deviation.
SCRUM VALUES
Commitment
to the team's goals
Focus
on the Sprint's work
Openness
about work and challenges
Respect
for each other's skills
Courage
to do the right thing
Notes: Explain that the pillars are the mechanism and the values are the behaviours. Without openness and courage, transparency collapses and inspection becomes theatre.

## Slide 6
THE SCRUM TEAM
Scrum Fundamentals | Onboarding
A small, self-managing team of typically ten or fewer people, with three distinct accountabilities
Source: The Scrum Guide, K. Schwaber & J. Sutherland (November 2020); team analysis
6
Product Owner
Maximises the value of the product
Owns and orders the Product Backlog
Develops and communicates the Product Goal
Is one person, not a committee
Represents stakeholder needs
Scrum Master
Establishes Scrum and team effectiveness
Coaches the team in self-management
Removes impediments to progress
Ensures events are held and productive
Helps the organisation adopt Scrum
Developers
Create a usable Increment every Sprint
Create the plan for the Sprint
Instil quality via the Definition of Done
Adapt their plan daily
Hold each other accountable
Notes: Stress that these are accountabilities, not job titles. "Developers" includes anyone doing the work: analysts, testers, designers, engineers. There are no sub-teams or hierarchies within the Scrum Team.

## Slide 7
SCRUM EVENTS
Scrum Fundamentals | Onboarding
Five events create a regular cadence; every event is timeboxed to keep the team focused
Source: The Scrum Guide, K. Schwaber & J. Sutherland (November 2020); team analysis
7
Event | Purpose | Who attends | Maximum timebox (1-month Sprint) | Typical (2-week Sprint)
The Sprint | Container for all other events; turns ideas into value | Scrum Team | 1 month | 2 weeks
Sprint Planning | Define why, what and how for the Sprint | Scrum Team (+ invited experts) | 8 hours | 4 hours
Daily Scrum | Inspect progress towards the Sprint Goal; adapt the plan | Developers | 15 minutes | 15 minutes
Sprint Review | Inspect the outcome and adapt the Product Backlog | Scrum Team + stakeholders | 4 hours | 2 hours
Sprint Retrospective | Plan ways to increase quality and effectiveness | Scrum Team | 3 hours | 1.5 hours
Note: Product Backlog refinement is an ongoing activity, not a formal event. As a guide, teams spend no more than about 10% of their capacity on it.
Notes: Timeboxes are maximums, not targets. Shorter Sprints usually mean proportionally shorter events. Our projects default to two-week Sprints unless agreed otherwise.

## Slide 8
SCRUM EVENTS | SPRINT PLANNING
Scrum Fundamentals | Onboarding
Sprint Planning answers three questions and ends with a committed Sprint Goal
Source: The Scrum Guide, K. Schwaber & J. Sutherland (November 2020); team analysis
8
1
Why is this Sprint valuable?
The Product Owner proposes how the product could increase its value; the whole team defines a Sprint Goal.
2
What can be Done this Sprint?
Developers select items from the Product Backlog, based on past performance, capacity and the Definition of Done.
3
How will the work get done?
Developers decompose items into small tasks, often of one day or less, and create their delivery plan.
OUTPUTS
Sprint Goal
A single objective that gives the Sprint coherence and focus
Sprint Backlog
The Sprint Goal, the selected items and the plan for delivering them
Notes: A good Sprint Goal is outcome-focused, e.g. "Customers can reset their own password" rather than "Complete stories 101 to 107". Give the group two minutes to rewrite a weak goal.

## Slide 9
SCRUM EVENTS | INSPECT AND ADAPT
Scrum Fundamentals | Onboarding
Three recurring events keep the team aligned daily and improving every Sprint
Source: The Scrum Guide, K. Schwaber & J. Sutherland (November 2020); team analysis
9
15 min
Daily Scrum
For the Developers, same time and place every working day.
Inspect progress towards the Sprint Goal
Adapt the Sprint Backlog as needed
Surface impediments early
Not a status report to management
≤ 4 h
Sprint Review
A working session with stakeholders, not a presentation.
Demonstrate what was accomplished
Discuss changes in the environment
Collaborate on what to do next
Adapt the Product Backlog
≤ 3 h
Sprint Retrospective
Concludes the Sprint; a safe space for the Scrum Team.
Review people, interactions, process and tools
Identify what went well and what did not
Agree the most impactful improvements
Add them to the next Sprint Backlog
Notes: Timeboxes shown are maxima for a one-month Sprint. Common trap: the Daily Scrum turning into a round-robin status update to the Scrum Master. Encourage the team to talk to each other about the goal.

## Slide 10
ARTEFACTS AND COMMITMENTS
Scrum Fundamentals | Onboarding
Each artefact has a commitment that provides focus and a measure of progress
Source: The Scrum Guide, K. Schwaber & J. Sutherland (November 2020); team analysis
10
ARTEFACT
COMMITMENT
Product Backlog
Emergent, ordered list of what is needed to improve the product; the single source of work.
Product Goal
The long-term objective the Scrum Team plans against.
Sprint Backlog
The plan by and for the Developers; a real-time picture of the Sprint's work.
Sprint Goal
The single objective for the Sprint, fixed once agreed.
Increment
A concrete, usable stepping stone towards the Product Goal; several may be created per Sprint.
Definition of Done
The quality standard every Increment must meet.
Notes: Emphasise the Definition of Done: if a backlog item does not meet it, it cannot be released or even presented at the Sprint Review. It returns to the Product Backlog.

## Slide 11
WORKING IN PRACTICE | BACKLOG ITEMS
Scrum Fundamentals | Onboarding
Well-formed backlog items are written from the user's perspective and are small enough to finish in a Sprint
Source: The Scrum Guide, K. Schwaber & J. Sutherland (November 2020); team analysis
11
EXAMPLE USER STORY
As a registered customer,
I want to
reset my password online,
so that
I can regain access without calling support.
Acceptance criteria
Reset link is sent to the registered email address
Link expires after 30 minutes
New password meets the security policy
Estimate: 3 story points
THE INVEST CHECKLIST
I
Independent
Can be built in any order
N
Negotiable
Details agreed with the team
V
Valuable
Delivers value to a user
E
Estimable
Team can size it
S
Small
Fits comfortably in a Sprint
T
Testable
Clear criteria to verify it
Notes: The Scrum Guide does not mandate user stories or story points; they are complementary practices we use on our projects. Exercise: in pairs, write one story for a feature on your current project and test it against INVEST.

## Slide 12
WORKING IN PRACTICE | TRACKING PROGRESS
Scrum Fundamentals | Onboarding
A Sprint burndown makes progress towards the Sprint Goal visible and prompts early action
Source: Illustrative data for a two-week Sprint; team analysis
12
ILLUSTRATIVE
Chart: Remaining work (story points)
| D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10
Ideal | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4
Actual | 40 | 39 | 35 | 34 | 33 | 27 | 22 | 15 | 9 | 3
1
Days 2–5: flat line
Work started but not finishing. Check for blockers or too much work in progress.
2
Days 6–9: steep drop
Items completed in batches. Encourage smaller items that flow daily.
3
Day 10: 3 points remain
Unfinished items return to the Product Backlog; discuss at the Retrospective.
Notes: Use metrics for the team's own learning, not for comparing teams. Velocity is a planning aid for a single team, not a performance target.

## Slide 13
WORKING IN PRACTICE | COMMON PITFALLS
Scrum Fundamentals | Onboarding
Most Scrum failures stem from a handful of recognisable anti-patterns that are easy to correct
Source: The Scrum Guide, K. Schwaber & J. Sutherland (November 2020); team analysis
13
WHAT WE SOMETIMES SEE
WHAT GOOD LOOKS LIKE
Daily Scrum becomes a status report to the manager
Developers plan their next 24 hours together around the Sprint Goal
Sprint scope keeps changing mid-Sprint
Sprint Goal stays fixed; scope is renegotiated only with the Product Owner
"Done" means code written, not tested or deployable
A shared Definition of Done applied to every item
Retrospective actions are agreed but never actioned
One or two improvements added to the next Sprint Backlog
Product Owner is unavailable or has no authority
An empowered Product Owner who makes ordering decisions
Notes: Ask participants which of these they have experienced before. Invite them to raise any of these patterns with the Scrum Master when they see them on our projects.

## Slide 14
YOUR FIRST 30 DAYS
Scrum Fundamentals | Onboarding
A structured first month takes new team members from observer to fully contributing Developer
Source: Onboarding programme guidance; team analysis
14
WEEK 1
Orient
Meet the Product Owner and Scrum Master
Read the Product Goal and Definition of Done
Observe all Scrum events
WEEK 2
Participate
Join Daily Scrums and speak to your work
Pair on a small backlog item
Get access to tools and boards
WEEK 3
Contribute
Take part in Sprint Planning
Own items through to Done
Join backlog refinement
WEEK 4
Improve
Share a fresh-eyes view in the Retrospective
Demo your work at the Sprint Review
Agree next steps with your Scrum Master
Success at day 30: you can explain the Sprint Goal, have delivered at least one item to Done, and have contributed to every Scrum event.
Notes: Adapt the plan to the individual; experienced practitioners may move faster. The Scrum Master is the first point of contact for any questions about the process.

## Slide 15
KEY TAKEAWAYS
Four things to remember from this module
01
Scrum is empirical
We plan in short cycles and adapt based on evidence, not assumptions.
02
Three accountabilities, one team
Product Owner, Scrum Master and Developers share one Product Goal.
03
Every event has a purpose
Five timeboxed events create transparency, inspection and adaptation.
04
Done means Done
Only work meeting the Definition of Done forms part of an Increment.
Questions? Speak to your Scrum Master | Further reading: scrumguides.org
Notes: Close with Q&A. Share the Scrum Guide link and point participants to Module 2 (Scrum in our delivery lifecycle).